## Q2 2026 Gantt
PROGRAM GUARDIAN — Q2 2026 Schedule ¦ P1 Priority ¦ RMS EP&T · AI Enterprise Performance · SOW v2
April 7 – June 30, 2026 ¦ Outcome headers reflect leadership deliverables · Subtasks reflect engineering work · ◆ = Acceptance Gate · Today = Apr 6
|  |  | APRIL 2026 |  |  |  | MAY 2026 |  |  |  | JUNE 2026
Task / Engineering Work | CAP | Status | W1 Apr 7 | W2 Apr 14 | W3 Apr 21 | W4 Apr 28 | W5 May 5 | W6 May 12 | W7 May 19 | W8 May 26 | W9 Jun 2 | W10 Jun 9 | W11 Jun 16 | W12 Jun 23 | W13 Jun 30
OUTCOME 1 · BA Suite Agents Callable by Guardian | [14 empty] | Q2 2026
CAP-02 · A2A / MCP — Agent wrapping, registry, integration contract
#25-26 Define sub-agent interface architecture + ADK AgentTool wrapper pattern | CAP-02 | Active
#26 Wrap PM Collaborator as ADK AgentTool (tool manifest + health check endpoint) | CAP-02 | Active
#26 Wrap ROADS Agent as ADK AgentTool (tool manifest + health check endpoint) | CAP-02 | Active
#26 Wrap RCCA + CAM Agents as ADK AgentTools | CAP-02 | Planned
#29 Register all 4 BA Suite agents in Guardian sub-agent registry (config-driven manifest, routing rules) | CAP-02 | Planned
#30 Integration test: Guardian routes risk query → ROADS via A2A; PM question → PM Collaborator via A2A | CAP-02 | Planned
◆ GATE — All 4 BA Suite agents callable by Guardian via A2A. Structured responses confirmed. Deployed to BA AD group. | CAP-01/02 | Gate | [6 empty] | ◆
OUTCOME 2 · Guardian Orchestrator Live with PM-Facing Portal | [14 empty] | Q2 2026
CAP-01 · ADK Orchestrator Agent — Initialize Guardian as Google ADK LlmAgent
#21 Initialize Program Guardian as ADK LlmAgent (system prompt, tool set, session config) | CAP-01 | Active
#22 Implement program state model using ADK (holds state, subscribes to sub-agent outputs) | CAP-01 | Active
#23 Persistent event loop: event ingestion, priority queue, workflow execution | CAP-01 | Planned
#24 Tool routing: Guardian delegates to correct sub-agent based on event type + registry rules | CAP-01 | Planned
CAP-02 · A2A + MCP Implementation — Full communication contract for agent delegation + external data
#27 Implement A2A delegation pattern: parallel fan-out / gather (ref: Google ADK multi-agent pattern) | CAP-02 | Active
#28 MCP server integration for external data sources: pmm, vemo, and others | CAP-02 | Planned
#29 Sub-agent registry: config-driven manifest, agent capabilities, protocol type (A2A/MCP), routing rules | CAP-02 | Planned
CAP-03 · Guardian Portal (UI + PM Interface) — React web app. NOT YET STARTED.
#31 Stand up React web app connected to Guardian state store and audit log (confirm stack) | CAP-03 | Planned
#32 Build Program Summary view (connected to specific program via authenticator) | CAP-03 | Planned
#33 Build Pending Actions panel — decision briefs with APPROVE / REJECT / DEFER controls | CAP-03 | Planned
#34 Build Audit Log view — filterable with drill-down to brief details | CAP-03 | Planned
#35 Conversational query interface: PM question → Guardian routes → sub-agent → cited response in portal | CAP-03 | Planned
#36 Program authenticator — toggle between programs; views re-render for selected program | CAP-03 | Planned
◆ GATE — Orchestrator live. Portal accessible. Guardian detects mock anomaly, routes to sub-agent, surfaces decision brief or pre-authorized action to PM. | CAP-01/02/03 | Gate | [9 empty] | ◆
OUTCOME 3 · Program Expert Pilot — Document Intelligence via Guardian | [14 empty] | Q2 anchor / Q3+ scale
CAP-04 · RAG / Info Retrieval — Vector store, doc ingestion, retrieval tool. Iterative — one program in Q2, more in Q3+.
#37 Provision Program Expert ADK agent + vector store backend (confirm: Vertex AI Vector Search or AlloyDB pgvector) | CAP-04 | Planned
#38 Define and build document ingestion pipeline — supports PDF, DOCX, XLSX minimum | CAP-04 | Planned
#39 Implement retrieval tool: natural language query + doc retrieval with citations | CAP-04 | Planned
#40 Register Program Expert in Guardian sub-agent registry with routing rules | CAP-04 | Planned
#41 Define program provisioning spec: configuration to stand up new Program Expert instance | CAP-04 | Planned
#42 Test on pilot program document set — document accuracy gaps before Q3 deployment [pilot scope — 1 program] | CAP-04 | Planned | [11 empty] | ▪ | ▪
◆ Q2 ANCHOR — Program Expert ingests real program docs, retrieves relevant passages with citations, callable by Guardian via A2A. Scales to more programs in Q3. | CAP-04 | Gate | [12 empty] | ◆
LOCKHEED MARTIN PROPRIETARY · Program Guardian SOW v2 · P1 Priority / Q2 2026 · Tasks 4-6 (P2/P3, Parallel Branch) not shown · Outcome 3 scales iteratively through Q3+

## Dependencies & Notes
PROGRAM GUARDIAN — Q2 2026 ¦ Dependencies, Open Items & Acceptance Criteria
OUTCOME FRAMING NOTE
Why outcomes, not tasks/CAPs? | Tasks answer 'what are we delivering.' CAPs answer 'how.' Leadership sees outcomes. Contractor/engineering uses CAP detail. This schedule shows both — outcomes as headers, CAPs as subtasks.
Outcome 3 is iterative | Program Expert does NOT complete in Q2. Q2 anchor = one pilot program tested and callable via Guardian. Q3+ = additional programs onboarded using the provisioning spec. 'Done' for Program Expert is a moving target by design.
SEQUENCING / DEPENDENCIES
Outcome 1 → Outcome 2 | BA Suite agent wrappers must be complete before Guardian can demonstrate end-to-end orchestration (Task 1 gate feeds Task 2 start)
CAP-02 before registry | A2A/MCP interface contract must be finalized before sub-agent registry is populated (#29)
CAP-01 before Portal | Guardian state store must exist before CAP-03 React app can connect to it
Portal parallel start | CAP-03 can begin W4 in parallel with orchestrator build — no hard blocker per SOW
Outcome 3 parallel | Program Expert provisioning (CAP-04) begins W7 in parallel with Portal completion
OPEN ITEMS / FLAGS
Portal stack | Task #31: 'React — confirm stack?' — decision needed before W4 start
Vector store | Task #37: Vertex AI Vector Search vs AlloyDB pgvector — confirm before W7
Program volunteer | Task 3 requires at least one program to volunteer a document set for pilot testing
CAP-05 (Pre-Auth Actions) | Flagged by Sam — needs more work. NOT in Q2 schedule. Target Q3 2026.
CAP-06 (PM Approval Workflow) | Flagged by Sam — needs more work. NOT in Q2 schedule. Target Q4 2026.
ACCEPTANCE CRITERIA BY GATE
Outcome 1 Gate (W7) | All 4 BA Suite agents callable by Guardian via A2A. Guardian routes a risk query to ROADS and a PM question to PM Collaborator, receiving structured responses both times. Deployed and available to BA AD group.
Outcome 2 Gate (W10) | Guardian orchestrator live. BA Suite connected. Portal accessible by PM. Guardian detects a mock anomaly, routes to appropriate sub-agent, synthesizes findings, and either executes a pre-authorized action or surfaces a decision brief to the PM.
Outcome 3 Q2 Anchor (W13) | Program Expert ingests a real program document set, correctly answers 5 test queries with source citations, and is callable by Guardian via A2A. A new program can be onboarded following the provisioning spec without core code changes.
P2/P3 TASKS — NOT IN THIS SCHEDULE
Task 4 — Program Health Agent | Q3 2026 · Parallel branch · Multi-variable EAC/EVMS financial health · connects to vemo/pmm · hackathon prototype
Task 5 — PRISM Systemic Issue Automation | Q3/Q4 2026 · Parallel branch · Cross-program risk patterns · $1-3M NFRO avoidance estimate · hackathon prototype
Task 6 — Augmented Independent Review | Q4 2026 · Parallel branch · Pre-review automation + panel scheduling · $500K/yr, ~2K hrs saved · hackathon prototype