## Q2 2026 Gantt
PROGRAM GUARDIAN — Q2 2026 Schedule ¦ P1 Priority Tasks ¦ RMS EP&T · AI Enterprise Performance · SOW v2
April 7 – June 30, 2026 ¦ ■ Task1/BA Suite ■ CAP-01 ADK Orch ■ CAP-02 A2A/MCP ■ CAP-03 Portal ■ Task3 Program Expert ◆ Milestone/Gate Today = Apr 6 (shaded)
|  |  | APRIL 2026 |  |  |  | MAY 2026 |  |  |  | JUNE 2026
Task / Engineering Work | CAP | Status | W1 Apr 7 | W2 Apr 14 | W3 Apr 21 | W4 Apr 28 | W5 May 5 | W6 May 12 | W7 May 19 | W8 May 26 | W9 Jun 2 | W10 Jun 9 | W11 Jun 16 | W12 Jun 23 | W13 Jun 30
TASK 1 · Business Acumen Suite · Q2 2026 ¦ Wrap 4 agents as ADK AgentTools → register in sub-agent registry → validate end-to-end
#25-26 Define sub-agent interface architecture + ADK AgentTool wrapper pattern | CAP-02 | Active
#26 Wrap PM Collaborator as ADK AgentTool (tool manifest + health check endpoint) | CAP-02 | Active
#26 Wrap ROADS Agent as ADK AgentTool (tool manifest + health check endpoint) | CAP-02 | Active
#26 Wrap RCCA + CAM Agents as ADK AgentTools | CAP-02 | Planned
#29 Register all 4 BA Suite agents in Guardian sub-agent registry (config-driven manifest, routing rules) | CAP-02 | Planned
#30 Integration test: Guardian routes risk query → ROADS agent via A2A; PM question → PM Collaborator via A2A | CAP-02 | Planned
◆ MILESTONE — Task 1 Acceptance: All 4 BA agents callable via A2A. Guardian routes queries successfully. Deployed to BA AD group. | CAP-01/02 | Gate | [6 empty] | ◆
CAP-01 · ADK Orchestrator Agent · TASK 2 ¦ Stand up Guardian as Google ADK LlmAgent with persistent event loop and program state model
#21 Initialize Program Guardian as ADK LlmAgent (system prompt, tool set, session config) | CAP-01 | Active
#22 Implement program state model using ADK (holds program state, subscribes to sub-agent outputs) | CAP-01 | Active
#23 Persistent event loop: event ingestion, priority queue, workflow execution | CAP-01 | Planned
#24 Tool routing: Guardian delegates to correct sub-agent based on event type and registry rules | CAP-01 | Planned
CAP-02 · A2A + MCP Implementation · TASKS 1, 2, 3 ¦ A2A governs agent delegation; MCP governs external tool/data source integration (pmm, vemo)
#27 Implement A2A delegation pattern: parallel fan-out / gather (ref: Google ADK multi-agent pattern) | CAP-02 | Active
#28 MCP server integration for external data: pmm, vemo, and other data sources | CAP-02 | Planned
#29 Build sub-agent registry: config-driven manifest with agent capabilities, protocol type (A2A/MCP), routing rules | CAP-02 | Planned
◆ MILESTONE — CAP-01 + CAP-02 Acceptance: Guardian orchestrator live, event ingestion operational, BA Suite via A2A, mock MCP tool incorporated into program state. | CAP-01/02 | Gate | [6 empty] | ◆
CAP-03 · Guardian Portal (UI + PM Interface) · TASK 2 ¦ React web app — program summary, pending actions, audit log, conversational query. NOT YET STARTED.
#31 Stand up React web app connected to Guardian state store and audit log (confirm stack) | CAP-03 | Planned
#32 Build Program Summary view (connected to specific program via program authenticator) | CAP-03 | Planned
#33 Build Pending Actions panel — decision briefs with APPROVE / REJECT / DEFER controls | CAP-03 | Planned
#34 Build Audit Log view — filterable with drill-down to brief details | CAP-03 | Planned
#35 Conversational query interface: PM question → Guardian routes to sub-agent → cited response surfaced in portal | CAP-03 | Planned
#36 Program authenticator — toggle between programs; views re-render for selected program | CAP-03 | Planned
◆ MILESTONE — Task 2 Acceptance: Portal loads program state from Guardian. PM approves a decision brief. Audit log updates. Conversational query routes to sub-agent. | CAP-03 | Gate | [9 empty] | ◆
TASK 3 · Program Expert (Q2 Ramp) · CAP-04 ¦ Begin RAG build in parallel with Task 2. Vector store, doc ingestion pipeline, retrieval tool. Full deployment Q2/Q3.
#37 Provision Program Expert as ADK agent with vector store backend (confirm: Vertex AI Vector Search, AlloyDB pgvector, or equivalent) | CAP-04 | Planned
#38 Define and build document ingestion pipeline — supports PDF, DOCX, XLSX at minimum | CAP-04 | Planned
#39-40 Implement retrieval tool (NL query + doc retrieval) + register Program Expert in Guardian sub-agent registry | CAP-04 | Planned
◆ Q2 CLOSE — Guardian orchestrator + BA Suite + Portal operational. Program Expert RAG pipeline established. Ready for Q3 production testing on real program docs. | CAP-04 | Gate | [12 empty] | ◆
LOCKHEED MARTIN PROPRIETARY · Program Guardian SOW v2 · RMS EP&T AI Enterprise Performance · P1 Priority Tasks Only · Tasks 4-6 (P2/P3) not shown

## Dependencies & Notes
PROGRAM GUARDIAN — Q2 2026 Dependencies & Notes
SEQUENCING LOGIC
Task 1 → Task 2 | BA Suite agent wrappers (CAP-01 #21) must be complete before Guardian can demonstrate end-to-end orchestration
CAP-02 before Registry | A2A/MCP interface contract must be finalized before sub-agent registry is populated
CAP-01 before Portal | Guardian state store must exist before CAP-03 React app can connect to it
Portal parallel start | CAP-03 development can begin in W4 in parallel with orchestrator — no hard blocker
Task 3 parallel | Program Expert provisioning (CAP-04) begins W7 in parallel with Portal completion
OPEN ITEMS / FLAGS
CAP-05 (Pre-Auth Actions) | Flagged by Sam as needing more work — NOT in Q2 schedule. Target Q3 2026.
CAP-06 (PM Approval Workflow) | Flagged by Sam as needing more work — NOT in Q2 schedule. Target Q4 2026.
Portal stack confirmation | Task #31 notes 'React — confirm stack?' — stack decision needed before W4 start
Vector store decision | Task #37 notes Vertex AI Vector Search vs AlloyDB pgvector — confirm before W7
Program volunteer needed | Task 3 requires at least one program to volunteer a document set for initial production testing
KEY ACCEPTANCE CRITERIA
Task 1 Gate (W7) | All 4 BA Suite agents callable by Guardian via A2A. Guardian routes a risk query to ROADS and a PM question to PM Collaborator, receiving structured responses both times. Deployed to BA AD group.
CAP-01/02 Gate (W7) | Guardian calls all Phase 1 sub-agents via A2A and at least one MCP tool, handles timeout gracefully, produces consolidated state update from multi-source outputs.
Task 2 Gate (W10) | Guardian orchestrator live. BA Suite connected. Portal accessible by PM. Guardian detects a mock anomaly, routes to appropriate sub-agent, synthesizes findings, and either executes a pre-authorized action or surfaces a decision brief to the PM.
Q2 Close (W13) | Guardian orchestrator + BA Suite + Portal fully operational. Program Expert RAG pipeline established and callable by Guardian via A2A. Ready for Q3 production testing.
TASKS NOT IN THIS SCHEDULE (P2/P3)
Task 4 — Program Health Agent | Q3 2026 · Parallel/Incremental branch · multi-variable EAC/EVMS financial health · connects to vemo/pmm
Task 5 — PRISM Systemic Issue Automation | Q3/Q4 2026 · Parallel/Incremental branch · cross-program risk patterns · $1-3M NFRO avoidance estimate
Task 6 — Augmented Independent Review | Q4 2026 · Parallel/Incremental branch · pre-review automation · $500K/yr, ~2K hrs saved