## Q2 2026 Schedule
Program Guardian — Schedule and Staffing ¦ Release One ¦ Q2 2026 ¦ RMS EP&T · AI Enterprise Performance
| Apr-26 |  |  |  | May-26 |  |  |  | Jun-26
| W1 Apr 7 | W2 Apr 14 | W3 Apr 21 | W4 Apr 28 | W5 May 5 | W6 May 12 | W7 May 19 | W8 May 26 | W9 Jun 2 | W10 Jun 9 | W11 Jun 16 | W12 Jun 23 | W13 Jun 30
Program Guardian Release One | [12 empty] | ◆
Outcome 1: BA Suite Agents Callable by Guardian | [6 empty] | ◆
MILESTONE — Acceptance: All 4 BA agents callable via A2A. Full communication contract between Program Guardian and sub-agents. A2A governs agent-to-agent delegation; MCP governs external tool and data source integration. Deployed to BA AD group.
Outcome 2: Guardian Orchestrator Live with PM-Facing Portal | [9 empty] | ◆
MILESTONE — CAP-01 + CAP-02 Acceptance: Guardian orchestrator live, event ingestion operational, BA Suite via A2A, mock MCP tool incorporated into program state. Portal accessible by PM — program summary, pending actions, audit log, conversational query.
Outcome 3: Program Expert Pilot on 1 Program (ADaRA) | [12 empty] | ◆
Q2 CLOSE — Guardian orchestrator + BA Suite + Portal operational. Program Expert (ADaRA) pipeline established. Ready for Q3 production testing on more programs and program documents. Capability scales iteratively — one program per onboarding cycle.
LOCKHEED MARTIN PROPRIETARY INFORMATION · Program Guardian SOW v2 · RMS EP&T AI Enterprise Performance · P1 Priority · March 2026

## Supporting Detail
PROGRAM GUARDIAN — Q2 2026 Supporting Detail
OUTCOME | CAPABILITY | WEEKS | ENGINEERING WORK
1 — BA Suite Callable | CAP-02 | W1–W2 | #25-26 Define sub-agent interface architecture + ADK AgentTool wrapper pattern
| CAP-02 | W1–W2 | #26 Wrap PM Collaborator as ADK AgentTool (tool manifest + health check endpoint)
| CAP-02 | W1–W3 | #26 Wrap ROADS Agent as ADK AgentTool
| CAP-02 | W3–W4 | #26 Wrap RCCA + CAM Agents as ADK AgentTools
| CAP-02 | W4–W5 | #29 Register all 4 agents in Guardian sub-agent registry (config-driven manifest, routing rules)
| CAP-02 | W6–W7 | #30 Integration test: Guardian routes queries to ROADS + PM Collaborator via A2A
◆ Milestone W7 |  |  | All 4 BA agents callable via A2A. Deployed to BA AD group.
2 — Guardian Orchestrator + Portal | CAP-01 | W1–W2 | #21 Initialize Guardian as ADK LlmAgent (system prompt, tool set, session config)
| CAP-01 | W1–W3 | #22 Implement program state model using ADK
| CAP-01 | W3–W5 | #23 Persistent event loop: event ingestion + priority queue
| CAP-01 | W5–W6 | #24 Tool routing: Guardian delegates to correct sub-agent based on event type
| CAP-02 | W1–W3 | #27 Implement A2A delegation pattern (parallel fan-out / gather)
| CAP-02 | W3–W6 | #28 MCP server integration: pmm, vemo, other external data sources
| CAP-02 | W4–W6 | #29 Sub-agent registry: config-driven manifest with routing rules
| CAP-03 | W4–W5 | #31 Stand up React web app connected to Guardian state store + audit log
| CAP-03 | W5–W6 | #32 Build Program Summary view
| CAP-03 | W6–W7 | #33 Pending Actions panel — APPROVE / REJECT / DEFER controls
| CAP-03 | W7–W8 | #34 Audit Log view — filterable with drill-down
| CAP-03 | W8–W9 | #35 Conversational query interface: PM → Guardian → sub-agent → cited response
| CAP-03 | W9–W10 | #36 Program authenticator — toggle between programs
◆ Milestone W10 |  |  | Guardian orchestrator live. Portal accessible by PM. Mock anomaly → sub-agent route → decision brief or pre-auth action.
3 — Program Expert Pilot (ADaRA) | CAP-04 | W7–W8 | #37 Provision Program Expert ADK agent + vector store backend (Vertex AI / AlloyDB — confirm)
| CAP-04 | W8–W9 | #38 Document ingestion pipeline — PDF, DOCX, XLSX
| CAP-04 | W10–W11 | #39-40 Retrieval tool + register Program Expert in Guardian sub-agent registry
| CAP-04 | W11–W13 | #41-42 Test on ADaRA document set; document accuracy gaps before Q3 deployment
◆ Q2 Close W13 |  |  | Program Expert pipeline established on ADaRA. Callable by Guardian via A2A. Scales to additional programs Q3+.
OPEN ITEMS / FLAGS
CAP-05 | Pre-Auth Actions | Q3 2026 | Flagged by Sam as needing more work. NOT in Q2 schedule.
CAP-06 | PM Approval Workflow | Q4 2026 | Flagged by Sam as needing more work. NOT in Q2 schedule.
Portal stack | CAP-03 #31 | Decide W3 | React confirmed? Decision needed before W4 portal build starts.
Vector store | CAP-04 #37 | Decide W6 | Vertex AI Vector Search vs AlloyDB pgvector — confirm before W7 provisioning.
Program volunteer | Task 3 | ASAP | Need ADaRA (or other program) to commit a document set for initial production testing.